## Sheet1
Bug # | Found by | Date | Summary/Description | Resolved by | Status? (fixed/open) | Date | Notes
1 | Francis P. |  | Clicking on the screen in some places causes the game to mess up and lag. | Open | Open | 2013-06-05
2 | Kevin D. | 2013-06-04 | You could still move around on the title screen. Resolved the issue | Kevin D. | Fixed | 2013-06-12
| Francis P. | 2013-06-03 | Heads were too large. Learned to love the size of our bodies. | Open | Open | 2013-06-12
| Josh G. | 2013-06-03 | It lagged when using one keyboard. We plugged in another keyboard | Francis P. | Fixed | 2013-06-10
| Kevin D. | 2013-06-03 | Music was glitchy. Didn't play | Josh G. | Fixed | 2013-06-10
| Lee S. | 2013-06-06 | we wanted multiple buttons to be pressed at the same time. We were only able to get one button working at a time and now we have 16. | Francis P. | Fixed | 2013-06-11